## Calendar (Overall)
Dezember			Januar			Februar			März			April			Mai
1	1a)		1			1			1			1			1
2			2	2b)		2			2			2			2
3			3			3			3			3			3
4			4			4			4			4			4
5	1b)		5			5			5			5			5
6			6			6			6			6			6
7			7			7			7			7			7
8			8			8			8			8			8
9			9			9			9			9			9
10			10			10			10			10			10
11			11			11			11			11			11
12			12			12			12			12			12
13			13			13	3b)		13			13			13
14			14			14			14			14			14
15			15			15			15			15			15
16	1c)		16	2c)		16			16			16	4a)		16
17			17			17			17			17			17
18			18			18			18			18			18
19	2a)		19			19			19	3d)		19			19
20			20	6a)		20			20			20			20
21			21			21			21	6b)		21			21
22			22			22			22			22			22
23			23			23			23			23			23
24			24			24			24			24			24
25			25			25			25			25			25
26			26			26			26			26			26
27			27			27	3c)		27			27			27
28			28			28			28			28			28
29			29			29			29			29			29
30			30	3a)					30			30	5)		30
31			31						31						31	6c)

## Tasks
Task		Time / [weeks]
1) Familiarization		2.5
	1a) Literature
	1b) Toolchain
	1c) Project Plan
2) Architecture and hardware design		6
	2a) Communication interface between HW blocks	2
	2b) Configuration interface for HW blocks	2
	2c) Data path between HW and SW	2
3) Implementation		11
	3a) Static version of communication interface	2
	3b) Reconfigurable version of communication interface	2
	3c) Configuration interface	3
	3d) HW/SW datapath	4
4) Evaluation		2
	4a) Performance evaluation of data paths	2
5) Documentation		5
6) Presentations
	6a) 1st short presentation
	6b) 2nd short presentation
	6c) Final presentation

## Iterations
Iteration 1: Communication interface between HW blocks
1) Basic architecture / - Define requirements / - Specify performance measures / - Evaluate possible design principles / - Choose design that best fits requirements / - Specify how to test resulting code	1 w
2) Block diagrams / - Identify entities / - Specify ports / - Draw block diagrams	1 w
3) Implementation / - Write code for entities	1 w
4) Simulation / - Write testbenches / - Generate testvectors / - Run simulations / debug code	1 w
5) Evaluation on Hardware / - Synthesize for hardware / - Run performance evaluation	1 w

## Calendar (Iteration 1)
Dezember			Januar			Februar			März			April			Mai
1			1			1			1			1			1
2			2	2)		2			2			2			2
3			3			3			3			3			3
4			4			4			4			4			4
5			5			5			5			5			5
6			6			6			6			6			6
7			7			7			7			7			7
8			8			8			8			8			8
9			9	3)		9			9			9			9
10			10			10			10			10			10
11			11			11			11			11			11
12			12			12			12			12			12
13			13			13			13			13			13
14			14			14			14			14			14
15			15			15			15			15			15
16			16	4)		16			16			16			16
17			17			17			17			17			17
18			18			18			18			18			18
19			19			19			19			19			19
20			20			20			20			20			20
21	1)		21			21			21			21			21
22			22			22			22			22			22
23			23	5)		23			23			23			23
24			24			24			24			24			24
25			25			25			25			25			25
26			26			26			26			26			26
27			27			27			27			27			27
28			28			28			28			28			28
29			29			29			29			29			29
30			30						30			30			30
31			31						31						31